## ProjSummary
EngagementID | Proj Desc (Input) | PM | PlannedHours | PlannedStart | PlannedEnd | Planned%Completion | Planned Value at this point | ActualStart | ActualEnd | BurntHours | Estimated Effort required to complete | Earned Value so far (as per effort hrs) | ExpectedEnd | CPI = Earned / Actual (as per effort hrs) | SPI = Earned / Planned | Open Impediments Count | Open Defects Count | Currency used (Input) | Total Labour Budget (Input) | Actual Labour Cost
ProjA | Happyness4All | kvasavaiah | 320 | 2019-01-01 | 2019-05-31 | 151.4% | 484.4037 | 2019-08-18 12:33 |  | 3 | 320 | 2.9721 | 2019-10-31 | 99.07% | 0.6136% | 1 | 1 | USD | 1500 | 0
Formulas:
Planned%Completion = NETWORKDAYS([PlannedStart],TODAY())/NETWORKDAYS([PlannedStart],[PlannedEnd])

## ProjPlan
TaskID (Input; No underscores pl.) | Task Desc (Input) | Owner (Input; ShortID) | Lead (Input; ShortID) | PlannedHours (Input) | PlannedStart (Input) | PlannedEnd (Input) | Planned%Completion | Planned Value at this point | Status | ActualStart | ActualEnd | BurntHours | Estimated Overrun Effort required to complete | Estimated Effort required to complete | Earned Value so far | ExpectedEnd | CPI = Earned / Actual | SPI = Earned / Planned | Open Impediments Count | Open Defects Count | Remarks
MyProjTask1 | TaskOne | KVASAVAIAH | PRABHU | 160 | 2019-08-01 | 2019-08-31 | 59.09% | 94.5455 |  | 2019-08-18 12:33 |  | 3 | 0 | 160 | 2.9448 | 1899-12-31 01:01 | 98.16% | 3.115% | 1 | 1
MyProjTask2 | TaskTwo | VIBEESH | PRABHU | 160 | 2019-09-10 | 2019-10-31 | -44.74% | -71.5789 |  |  |  | 0 | 0 | 160 | 0 | 1899-12-31 01:01 | #DIV/0! | 0%
Formulas:
Planned%Completion = NETWORKDAYS([PlannedStart (Input)],TODAY())/NETWORKDAYS([PlannedStart (Input)],[PlannedEnd (Input)])

## Resources
ResourceID (Input; ALL CAPS) | RoleID (Input) | Hourly Rate (Input) | Effort Hrs spent | Labor Cost so far | Note: Currency is: | USD
VIBEESH | PM | 1 |  | 0
KVASAVAIAH | PL | 1 |  | 0
PRABHU | Arhitect | 1 |  | 0
kvasavaiah | UnknownRole | 0 | 3

## Impediments
ImpedimentID | Impediment Desc | Severity (High/Medium/Low) | Owner (ShortID) | OpenedDate | Status | ExpectedEnd | ActualEnd | %Completed | BurntHours (sum of hrs booked) | Remarks
ImpdmtMyProjTask1_kvasavaiah20190818121254 | Access Not given |  | kvasavaiah |  |  |  |  | 0 | 0

## Defects
DefectID | Defect Desc | Severity (High/Medium/Low) | RaisedBy | Owner (ShortID) | OpenedDate | Status | ExpectedEnd | ActualEnd | %Completed | BurntHours (sum of hrs booked) | Remarks
DfctMyProjTask1_kvasavaiah20190818114942 | Screen is very slow |  |  | kvasavaiah |  |  |  |  | 0 | 0